## Why
Objective | Provide Enterprises with an opportunity to access insights from a defined data set

## What
App that can offer summarization, insights from Enterprise Knowledge Base

## How(Prod Blg)
Code | Mohamed Abul Hassan A
MVP | Feature Reference | Story | Detailed Description | Definition of Ready | Definition of Done | Status | Reviewed By | Passed / Not Passed | Planned Story Point | Actual Story Point | Difference b/w PSP & ASP | Delivered SP
MVP-1 | Project Planning & Backlog Creation | 1 - Outline steps and create backlog | App that can offer summarization, insights from Enterprise Knowledge Base | Access to project documentation (Product blog) | Clear steps outlined with a structured backlog (refer feature sheet) | Completed | Sriram R | Passed | 5 days | 7 days | 2 days
MVP-1 | Python Environment | 2- Set up Python Environment | Need to install necessary libraries like fitz,asyncio, langchain-community,langchain-core,langchain , faiss etc...(refer feature sheet AI001) | VS code , Python 3.11.9 , Listed libraries (refer feature sheet - AI001) | Successfully installed required libraries using the prepared text file. | Completed | Sriram R | Passed | 1 days | 1 days | 0 days
MVP-1 | Sambanova AI Model Integration (Part 1) | 3 - Set up Sambanova AI models connection (BE) | Set up connections to Meta model (llama3 - 405b) for generating summaries. | Sambanova API credentials, llama3-405b model , postman,necessary libraries and sample Inputs . (Refer Feature sheet AI002 - AI007) | Meta model (llama3 - 405b)connected, API tested with Postman, and models return expected summaries. | Completed | Sriram R | Passed | 3 days | 3 days | 0 days
MVP-1 | Custom prompt and Vectorstore | 4- Custom Prompt and Vectorstore | Creating a Custom prompt and Vectorstore using faiss | FAISS library, embedding model(all-MiniLM-L6-v2), document text | Vectors created using embedding model, stored locally using FAISS, and custom prompt generated. | Completed | Sriram R | Passed | 2 days | 2 days | 0 days
MVP-1 | Sambanova AI Model Integration (Part 2) | 5- Implement RAG with Sambanova models | Integrating RAG pipeline with Meta model (llama3 - 405b) and extract the relevant content | RAG pipeline initialized, sample query | RAG pipeline integrated with Meta model, generating data for user queries. | Completed | Sriram R | Passed | 3 days | 2 days | 1 days
MVP-1 | Database Structure Design | 6- Design database structure | Create a Structure(JSON) for storing summary , user query and response from the LLM in MongoDB. | Summary , user query and response from the LLM , pymongo library | Database structure is created, tested, and is ready for storing the summary ,user query and response from the LLM. | Completed | Sriram R | Passed | 2 | 2 days | 0 days
MVP-1 | Front-End Design | 7- Figma Design for Chat Interface | Create the FE design using Figma. | Figma Tool and Data Format | All pages and components for the chat interface designed in Figma. | TAKEN |  |  | 3
MVP-1 | React Chat Interface | 8 - Develop React Chat Interface | Build the chat interface using React based on the Figma design. | Figma Design for Chat Interface | The chat interface is fully implemented in React, with a perfect UI as per Figma design. | TAKEN |  |  | 7
MVP-1 | Front-End and Back-End Integration | 9 - Intergration of FE and BE | Connect the chat interface to BE for Data reterival , ensuring that RAG is applied to fetch relevant data | BE API available for connection and React environment set up | Chat interface is successfully connected with backend APIs. .Data is fetched and displayed in the user interface without issues | TO DO |  |  | 3
MVP-1 | Data Collection and Storage | 10 - Collecting and Storing the Fetched Data | Collect the Insights from the Docs using Sambanova Enterprise Reterival , and store to Mongo DB | FE and BE integration completed | Data is successfully collected using the Sambanova retrieval system and stored in MongoDB. | TO DO |  |  | 4
MVP-1 | Outcome Refinement | 11 - Refining the outcome | Achieving the desired output (Summarization and User can able to ask Q&A) | Data collection and storage process | Web application provides summarization and insights, Q&A functionality works smoothly. | TO DO |  |  | 2

## Defects
S. No | Points to Consider | Status
1 | Missing testing and bug fixing phase - it can be added | Done
2 | No. of Days planned/estimated to complete is not mentioned
3 | There are some complex DoD and DoR | Done
4 | Verify with Mentor regarding DoR | Done
5 | Feature Reference can be added | Done
6 | Story Points should be numbered | Done

## Sprint Plan
Sprint # | Start Date | End Date | Target | Status | Capacity SP | Planned SP | Delivered SP | Delta | Approved By | Learning | Reviewed By | Passed / Not Passed
0 | 2024-09-27 | 2024-10-03 | KICKOFF | Completed | 2.5 | 2.5 | 2.5 | 0
1 | 2024-10-04 | 2024-10-10 | Product Backlog | Completed | 2.5 | 2.5 | 2.5 | 0 |  | Product Backlog and working
2 | 2024-10-11 | 2024-10-17 | S2 , S3 | Completed | 2.5 | 2.5 | 2.5 | 0 |  | Llama model working
3 | 2024-10-18 | 2024-10-24 | S4 , S5 | Completed | 2.5 | 3.5 | 4 | 0.5 |  | Implementation of RAG
4 | 2024-10-25 | 2024-10-31 | S5 , S6 | Completed | 2.5 | 2.5 | 2.5 | 0 |  | Connecting DataBase
4 | 2024-11-01 | 2024-11-07 | S5 , S6 | Taken | 2.5 | 4
5 | 2024-11-08 | 2024-11-14 | S5 , S6 | Taken
6 | 2024-11-29 | 2024-12-05 | S5, S6 ,S7

## Feature
Scope | Feature Code | Category | Use Case | Output
MVP | AI001 | Necessary things for the environment | Requirements | VS code , Python 3.11.9 , Libraries - > (https://drive.google.com/file/d/1ld6ozplpEB5h9QcbOPKUQBo9DM6DiBPf/view?usp=sharing),Sambanova AI model (llama3 -405b , llama3-70b) , Embedding Model (all-MiniLM-L6-v2),Sambanova API key,MongoDB , Node.js
MVP | AI002 | Feature - I | Data as PDF | Summary of the PDF and Response from the LLM related to the user query
MVP | AI003 | Feature - II | Data as Document | Summary of the Document and Response from the LLM related to the user query
MVP | AI004 | Feature - III | Data as PPT | Summary of the PPT and Response from the LLM related to the user query
MVP | AI005 | Feature - IV | Data as EXCEL | Summary of the EXCEL and Response from the LLM related to the user query
MVP | AI006 | Feature - V | Data as Text | Summary of the Text and Response from the LLM related to the user query
MVP | AI007 | Feature - VI | Data as CSV | Summary of the CSV and Response from the LLM related to the user query
MVP | AI008 | Feature - VII | Data as JSON | Summary of the JSON and Response from the LLM related to the user query

## Tech
Component | Technology
Frontend | React framwork
Backend | Node.js, Python
Database | MongoDB,SQL, Vector DB
APIs used | SambaNova API
Cloud Platform | AWS, GCP, AZURE

## Q&A
Question | Answer | Status