## Why
Objective | Provide Enterprises with an opportunity to access insights from a defined data set

## What
App that can offer summarization, insights from Enterprise Knowledge Base

## How(Prod Blg)
Code | Mohamed Abul Hassan A
MVP | Feature Reference | Story | Detailed Description | Definition of Ready | Definition of Done | Status | Who | Planned Story Point | Actual Story Point | Difference b/w PSP & ASP | Delivered SP
MVP-1 | Project Planning & Backlog Creation | 1 - Outline steps and create backlog | App that can offer summarization, insights from Enterprise Knowledge Base | Access to project documentation and essential tools | Clear steps outlined, features finalized, and a backlog created. | Completed | MOHAMED ABUL HASSAN A | 7 | 9
MVP-1 | Sambanova AI Model Integration (Part 1) | 2 - Set up Sambanova AI models connection (BE) | Set up connections to Sambanova AI models for generating summaries, configure API calls for data generation. | Sambanova AI starter kit , API credentials from Sambanova, backend prepared to handle API requests, necessary libraries installed, and API configuration setup. | Sambanova AI models connected, API tested using Postman, and models return summaries as expected. | Completed | MOHAMED ABUL HASSAN A | 5 | 5
MVP-1 | Sambanova AI Model Integration (Part 2) | 3 - Implement RAG with Sambanova models | Retrieve relevant data from external sources using RAG, and feed it into Sambanova models for summary generation. | API keys to access external data sources, RAG pipeline prepared. | External data retrieved using RAG, integrated into Sambanova models for enhanced summaries, and functionality tested. | TAKEN | MOHAMED ABUL HASSAN A | 5 | 3
MVP-1 | Insights Generation | 4 -Implement insights generations | Configure models to extract key points and insights from the data using RAG . Insights generated by pulling additional relevant information from external data sources. | Sambanova AI models to generate a summary of data given by the user | Insights are being generated from the data through the configured models. Proper relevant data is generated. | TAKEN | MOHAMED ABUL HASSAN A | 2 | 2
MVP-1 | Database Structure Design | 5 - Design database structure | Create a Structure(JSON) for storing insights and summaries in MongoDB.The data is stored so that users can check their previous queries and view responses. | Output from LLM | Database structure is created, tested, and is ready for storing the processed insights and summaries efficiently. | TAKEN | MOHAMED ABUL HASSAN A | 2 | 1
MVP-1 | Front-End Design | 6- Figma Design for Chat Interface | Create the FE design using Figma. | Figma Tool and Data Format | All pages and components for the chat interface designed in Figma. | TAKEN | MOHAMED ABUL HASSAN A | 3
MVP-1 | React Chat Interface | 7 - Develop React Chat Interface | Build the chat interface using React based on the Figma design. | Figma Design for Chat Interface | The chat interface is fully implemented in React, with a perfect UI as per Figma design. | TAKEN | MOHAMED ABUL HASSAN A | 7
MVP-1 | Front-End and Back-End Integration | 8 - Intergration of FE and BE | Connect the chat interface to BE for Data reterival , ensuring that RAG is applied to fetch relevant data | BE API available for connection and React environment set up | Chat interface is successfully connected with backend APIs. .Data is fetched and displayed in the user interface without issues | TO DO | MOHAMED ABUL HASSAN A | 3
MVP-1 | Data Collection and Storage | 9 - Collecting and Storing the Fetched Data | Collect the Insights from the Docs using Sambanova Enterprise Reterival , and store to Mongo DB | FE and BE integration completed | Data is successfully collected using the Sambanova retrieval system and stored in MongoDB. | TO DO | MOHAMED ABUL HASSAN A | 4
MVP-1 | Outcome Refinement | 10 - Refining the outcome | Achieving the desired output (Summarization and User can able to ask Q&A) | Data collection and storage process | Web application provides summarization and insights, Q&A functionality works smoothly. | TO DO | MOHAMED ABUL HASSAN A | 2

## Defects
S. No | Points to Consider | Status
1 | Missing testing and bug fixing phase - it can be added | Done
2 | No. of Days planned/estimated to complete is not mentioned
3 | There are some complex DoD and DoR | Done
4 | Verify with Mentor regarding DoR | Done
5 | Feature Reference can be added | Done
6 | Story Points should be numbered | Done

## Sprint Plan
Sprint # | Start Date | End Date | Target | Status | Approved By
0 | 2024-09-27 | 2024-10-03 | KICKOFF | Completed
1 | 2024-09-27 | 2024-10-10 | Product Backlog | Completed
2 | 2024-10-11 | 2024-10-17 | S 2 | Completed
3 | 2024-10-18 | 2024-10-24 | S3 , S4 , S5 | Completed
4 | 2024-10-25 | 2024-10-31 | S6 , S7
4
5

## Feature
Scope | Feature Code | Category | Use Case | Output
MVP | AI001 | AI Starter Kit
MVP | AI002 | AI Starter Kit
MVP | AI003 | AI Starter Kit
MVP | AI004 | AI Starter Kit
MVP | AI005 | AI Starter Kit

## Tech
Component | Technology
Frontend | React framwork
Backend | Node.js, Python
Database | MongoDB,SQL, Vector DB
APIs used | SambaNova API
Cloud Platform | AWS, GCP, AZURE

## Q&A
Question | Answer | Status